## Sprint 1 Burndown Chart
RUSH RACING BURNDOWN CHART
User story | Description | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | As a user, I want to be able to view all game modes by pressing the play button so that I can decide which game mode I want to play. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2 | As a user, I want to have a back button so that I can navigate around the menus | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
3 | As a user, I would like to be able to adjust or mute the volume of the game, so I can play with the sound off. | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
4 | As a user, I want to be able to pause the game so that I can be away from my device without having to lose or quit the current game | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
5 | As a user, I want to be able to create a user profile so that I can save my progress and continue from it at a later date | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
6 | As a user, I want to be able to quit the current game so that I can go back to the main menu and choose a different game mode. | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
7 | As a user, I want to have a settings menu so that I can change settings such as volume level, graphics level etc | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
8 | As a user, I want to view available maps so that I can see which track I would like to play on | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
9 | As a user, I would like to view available upgrades for my cars so I can decide whether to purchase an upgrade or not. | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
10 | As a user, I would like to be able to spend my earned currency on cars and upgrades so that I can improve my performance at future races | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
11 | As a user, I want to have a HUD (heads up display) overlay so that I can view statistics of the current game | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0
12 | As a user, I want to have a mini-map during a race to help give me an approximation of the track | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
| Story Points remaining | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 68 | 54 | 54 | 51 | 51 | 51
| Ideal | 73 | 68.1333 | 63.2667 | 58.4 | 53.5333 | 48.6667 | 43.8 | 38.9333 | 34.0667 | 29.2 | 24.3333 | 19.4667 | 14.6 | 9.7333 | 4.8667 | 0
Total points | Days
73 | 15
73 | 14
73 | 13
73 | 12
73 | 11
73 | 10
73 | 9
73 | 8
73 | 7
73 | 6
68 | 5
54 | 4
54 | 3
51 | 2
51 | 1
Sprint days