## Sprint 1 Burndown Chart
RUSH RACING BURNDOWN CHART
User story | Description | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | As a user, I want to be able to view all game modes by pressing the play button so that I can decide which game mode I want to play. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2 | As a user, I want to have a back button so that I can navigate around the menus | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
3 | As a user, I would like to be able to adjust or mute the volume of the game, so I can play with the sound off. | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
4 | As a user, I want to be able to pause the game so that I can be away from my device without having to lose or quit the current game | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
5 | As a user, I want to be able to create a user profile so that I can save my progress and continue from it at a later date | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
6 | As a user, I want to be able to quit the current game so that I can go back to the main menu and choose a different game mode. | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
7 | As a user, I want to have a settings menu so that I can change settings such as volume level, graphics level etc | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
8 | As a user, I want to view available maps so that I can see which track I would like to play on | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
9 | As a user, I would like to view available upgrades for my cars so I can decide whether to purchase an upgrade or not. | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
10 | As a user, I would like to be able to spend my earned currency on cars and upgrades so that I can improve my performance at future races | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
11 | As a user, I want to have a HUD (heads up display) overlay so that I can view statistics of the current game | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0
12 | As a user, I want to have a mini-map during a race to help give me an approximation of the track | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0
| Story Points remaining | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 73 | 68 | 54 | 54 | 51 | 49 | 24
| Ideal | 73 | 68.1333 | 63.2667 | 58.4 | 53.5333 | 48.6667 | 43.8 | 38.9333 | 34.0667 | 29.2 | 24.3333 | 19.4667 | 14.6 | 9.7333 | 4.8667 | 0
Total points | Days
73 | 15
73 | 14
73 | 13
73 | 12
73 | 11
73 | 10
73 | 9
73 | 8
73 | 7
73 | 6
68 | 5
54 | 4
54 | 3
51 | 2
49 | 1
Sprint days
Reflection of progress of sprint 1 burndown chart:
Our sprint 1 burndown chart is not as great as we expected.
Firstly, we underestimated the time that project setup would take. The first week of development was spent setting up as well as ironing out any problems we had with Unity or Github. User story development could only be started around the end of the first week. Secondly, as the semester gets busier and other papers and assignments to juggle, testing user stories was low priority in some cases and testing was not complete as straight as user stories were moved into the testing column. Sometimes, we had to focus on getting our development user stories complete. Thirdly, we have some user stories that were not complete that will be brought into sprint 2. That is why the burndown chart does not touch the ground. From next sprint, we are going to make sure to prioritise user story testing as soon as they are ready. This also involves better communication between the developer and tester to let each other know the status of user stories.
With a better understanding of time estimation of development, we will ensure to practice better time management for this project and hopefully have a burndown chart that sticks closer to the ideal trend for sprint 2.